CERA MEDICAL  /  STACK & SCALE

Full Platform
10-Day Delivery Workbook

Developer 01 — Product & Frontend

Owns the customer-facing CERA platform, CMS presentation, forms, accessibility, and customer dashboard.

| Delivery control | Agreed working rule |
| --- | --- |
| Programme target | Complete the full CERA first-release platform in ten intense working days. Work is sliced vertically and integrated daily. |
| Branch base | All feature branches start from develop. main is production-only. No direct pushes to protected branches. |
| Required approvals | One PR approval minimum; two for authentication, database migrations, secrets, deployment, or security changes. |
| Definition of launch | Public services/blog, CMS, secure enquiry, customer status, staff workflow, Zoho, Resend, Authentik, R2, monitoring, backup and documented deployment all work in staging and production. |

1. Recommended project decisions

| Decision | Recommended direction |
| --- | --- |
| Customer journey | Browse public services and blog posts; submit a secure service enquiry; optionally create an account to view enquiry status and updates. Online payment is not in v1 until CERA selects a payment provider in writing. |
| Staff roles | Customer; Content Editor; Operations/Support; Administrator. Authentik enforces role-based access. |
| Data boundary | Collect only name, email, phone, selected service, message, consent, and enquiry status. Do not collect diagnosis, medical history, prescriptions, or health documents in v1. |
| Zoho records | Create/update Lead or Contact with full name, email, phone, selected service, source, consent timestamp, enquiry ID, owner, and status. |
| Content approval | CERA nominates one Content & Clinical Approver. No health claim, service description, blog, or public pricing is published without that person’s written approval. |
| Release approval | Dev 3 approves technical readiness. CERA’s nominated Product Owner approves staging/UAT. Production needs both approvals in GitHub. |
| Account ownership | CERA owns and pays all vendor accounts: Hetzner, Cloudflare, R2, GitHub, Resend, Zoho, domain, and backups. Developers receive only necessary role-based access. |
| Jurisdiction | Swabi, Khyber Pakhtunkhwa, Pakistan. |

2. Your ownership and boundaries

| Area | Your responsibility |
| --- | --- |
| Primary modules | Next.js public platform; shared UI; Payload CMS presentation; service pages; blog; enquiry flow; customer dashboard. |
| Key integrations | Consumes Vendure/service APIs; presents Authentik login; uploads through approved R2 flow; surfaces Resend confirmation states. |
| Review focus | Accessibility, mobile experience, error states, consent copy, public content, and API contract use. |

3. Daily collaboration routine

09:30 — 15-minute stand-up: yesterday, today, blockers, files likely to conflict.

Before coding — read the assigned issue, acceptance criteria, and shared contract/type.

During coding — work only on the named branch; do not edit another developer’s active module without agreement.

Before PR — run lint, type-check, relevant tests, and manual local verification.

PR review — one approval minimum; two approvals for auth, database migrations, secrets, deployment, or security changes.

End of day — update the GitHub Issue, post staging link/test evidence where available, and name any hand-off needed tomorrow.

4. Ten-day build schedule

Each day ends with a pushed branch, updated issue, test evidence, and a clear hand-off. If a task cannot be completed, cut non-critical polish—not security, data ownership, test coverage, or release controls.

| Day | Branch | Build work | Done | Hand-off |
| --- | --- | --- | --- | --- |
| 1 | chore/web-foundation | Create apps/web structure, routing, shared UI package, fonts, base layout, error boundaries, and local environment. | Public shell runs locally; route map and UI conventions committed. | Confirm API route names and shared types with Dev 2. |
| 2 | feat/ui-design-system | Build responsive navigation, footer, buttons, forms, cards, loading states, empty states, and accessibility baseline. | Reusable design system and Storybook-like component examples. | Give Dev 2 exact input/output shapes needed by forms. |
| 3 | feat/cms-public-pages | Connect Payload CMS for homepage, about, policies, navigation, and editable page sections. | Editors can update approved public pages in staging. | Ask CERA for content owner and approved copy/assets. |
| 4 | feat/services-catalogue | Create service listing/detail pages consuming the Dev 2 catalogue contract; add filters, CTA, SEO metadata. | Services render from real staging data. | Dev 2 supplies seed service catalogue and slugs. |
| 5 | feat/blog-and-seo | Build blog listing/article templates, author/date, media handling, metadata, sitemap/robots rules, and CMS preview. | Approved blog content can be previewed and published. | Dev 3 confirms Cloudflare/Caddy cache rules. |
| 6 | feat/enquiry-form | Build validated enquiry form, consent checkbox, success/error states, and enquiry-status entry point. | User can send a test enquiry from staging. | Dev 2 connects API; Dev 3 supplies Resend/CORS settings. |
| 7 | feat/customer-dashboard | Build Authentik login entry, protected dashboard shell, profile view, and enquiry-status timeline. | Customer sees only their own test enquiries. | Dev 2 supplies customer-status API; Dev 3 validates roles. |
| 8 | test/web-e2e-flows | Write browser tests for browse → enquiry → email confirmation → sign-in → status. Test mobile and accessibility. | E2E evidence linked to release issue. | Report defects as GitHub Issues, not chat-only notes. |
| 9 | fix/uat-frontend | Resolve CERA UAT issues, improve public copy/layout only after Content & Clinical Approver approval. | All frontend UAT defects closed or accepted for later release. | No unrelated redesigns after release freeze. |
| 10 | release/web-v1.0.0 | Verify production build, smoke-test public pages, forms, CMS publishing, login, and dashboard after release. | Frontend release checklist signed in GitHub. | Hand over page/content editing guide to CERA. |

5. Integration contracts and hand-offs

| Direction | Working agreement |
| --- | --- |
| Read from Dev 2 | Service catalogue, enquiry creation/status, customer profile/status, Zoho/Resend event results. |
| Read from Dev 3 | Auth URLs/roles, environment variables, Caddy routes, staging URL, monitoring rules. |
| Provide to team | UI field requirements, component states, screenshots, browser test cases, public-page acceptance criteria. |

6. Git and pull-request rules

Use conventional commits: feat(scope): description; fix(scope): description; test(scope): description; ci: description.

Keep PRs single-purpose. Include issue link, screenshots for UI work, tests run, migration impact, and rollback note where relevant.

Before PR: git fetch origin; git rebase origin/develop; resolve conflicts; run the relevant tests; push only your branch.

Never commit .env files, passwords, API keys, backups, real customer data, or production database dumps.

A database migration must be reversible or backward-compatible and reviewed by Dev 2 and Dev 3.

7. Day-10 release and post-launch responsibility

Freeze new feature work after Day 8. Only UAT defects, security fixes, and release documentation are allowed.

Create release/v1.0.0 from develop; deploy it to staging; run the complete smoke-test checklist.

CERA Product Owner records staging approval in the release issue; Dev 3 records technical approval.

Merge release/v1.0.0 to main, create annotated tag v1.0.0, and deploy the immutable image.

Watch GlitchTip, health checks, logs, Resend delivery, R2 access, and Zoho sync for the first 24 hours.

If a critical issue appears, create hotfix/<name> from main, test, release, and merge the fix back to develop.

Named developer: ______________________________     Date assigned: ______________________________