CERA MEDICAL  /  STACK & SCALE

Full Platform
10-Day Delivery Workbook

Developer 02 — Commerce, Data & Integrations

Owns service catalogue/data, Vendure, PostgreSQL migrations, customer/enquiry APIs, Resend, and Zoho.

| Delivery control | Agreed working rule |
| --- | --- |
| Programme target | Complete the full CERA first-release platform in ten intense working days. Work is sliced vertically and integrated daily. |
| Branch base | All feature branches start from develop. main is production-only. No direct pushes to protected branches. |
| Required approvals | One PR approval minimum; two for authentication, database migrations, secrets, deployment, or security changes. |
| Definition of launch | Public services/blog, CMS, secure enquiry, customer status, staff workflow, Zoho, Resend, Authentik, R2, monitoring, backup and documented deployment all work in staging and production. |

1. Recommended project decisions

| Decision | Recommended direction |
| --- | --- |
| Customer journey | Browse public services and blog posts; submit a secure service enquiry; optionally create an account to view enquiry status and updates. Online payment is not in v1 until CERA selects a payment provider in writing. |
| Staff roles | Customer; Content Editor; Operations/Support; Administrator. Authentik enforces role-based access. |
| Data boundary | Collect only name, email, phone, selected service, message, consent, and enquiry status. Do not collect diagnosis, medical history, prescriptions, or health documents in v1. |
| Zoho records | Create/update Lead or Contact with full name, email, phone, selected service, source, consent timestamp, enquiry ID, owner, and status. |
| Content approval | CERA nominates one Content & Clinical Approver. No health claim, service description, blog, or public pricing is published without that person’s written approval. |
| Release approval | Dev 3 approves technical readiness. CERA’s nominated Product Owner approves staging/UAT. Production needs both approvals in GitHub. |
| Account ownership | CERA owns and pays all vendor accounts: Hetzner, Cloudflare, R2, GitHub, Resend, Zoho, domain, and backups. Developers receive only necessary role-based access. |
| Jurisdiction | Swabi, Khyber Pakhtunkhwa, Pakistan. |

2. Your ownership and boundaries

| Area | Your responsibility |
| --- | --- |
| Primary modules | Vendure/service catalogue; PostgreSQL data model; shared contracts; enquiry workflow; customer status API; Zoho and Resend integrations. |
| Key integrations | Authentik subject/role data from Dev 3; Next.js forms and dashboard from Dev 1. |
| Review focus | Data validation, permission checks, migrations, idempotent webhooks, retry behaviour, and test coverage. |

3. Daily collaboration routine

09:30 — 15-minute stand-up: yesterday, today, blockers, files likely to conflict.

Before coding — read the assigned issue, acceptance criteria, and shared contract/type.

During coding — work only on the named branch; do not edit another developer’s active module without agreement.

Before PR — run lint, type-check, relevant tests, and manual local verification.

PR review — one approval minimum; two approvals for auth, database migrations, secrets, deployment, or security changes.

End of day — update the GitHub Issue, post staging link/test evidence where available, and name any hand-off needed tomorrow.

4. Ten-day build schedule

Each day ends with a pushed branch, updated issue, test evidence, and a clear hand-off. If a task cannot be completed, cut non-critical polish—not security, data ownership, test coverage, or release controls.

| Day | Branch | Build work | Done | Hand-off |
| --- | --- | --- | --- | --- |
| 1 | chore/contracts-and-data-model | Create packages/contracts, PostgreSQL schema, migration policy, seed fixtures, and status enum definitions. | Shared contracts compile; Dev 1 can mock catalogue/enquiry data. | Freeze initial field names before UI work begins. |
| 2 | feat/vendure-service-catalogue | Configure Vendure service/products, categories, pricing display data, slugs, images/metadata references, and seed catalogue. | Staging API returns services reliably. | Dev 1 consumes catalogue endpoints. |
| 3 | feat/enquiry-api | Create secure enquiry endpoint: validate input, save record, apply consent timestamp, issue reference ID, and prevent duplicate submission. | Real staging enquiry is stored and testable. | Publish request/response contract to Dev 1. |
| 4 | feat/zoho-lead-sync | Create idempotent Zoho Lead/Contact sync with source, service interest, consent, enquiry ID, owner, and failure logging. | A test enquiry appears once in Zoho with correct fields. | Dev 3 stores secrets; Dev 1 verifies user-facing outcome. |
| 5 | feat/resend-notifications | Send enquiry receipt to customer and operational notification to CERA; handle delivery failure without losing enquiry. | Test emails arrive and are logged. | Use Resend sandbox/test domain until CERA verifies production domain. |
| 6 | feat/customer-api | Connect Authentik identity to customer record; provide ‘my enquiries’ and detail/status APIs with strict ownership checks. | Customer cannot read another customer’s data. | Dev 1 integrates dashboard against staging API. |
| 7 | feat/operations-api | Create staff-only enquiry status/update workflow, audit-friendly timestamps, and approved operational status transitions. | Operations test user can manage assigned enquiries. | Dev 3 validates Authentik role claims. |
| 8 | test/integration-flows | Write integration tests for migrations, enquiry validation, Zoho retry/idempotency, Resend failure, and authorisation. | CI tests protect core data and integrations. | Run backup/restore exercise with Dev 3. |
| 9 | fix/uat-integrations | Fix UAT defects; reconcile failed test syncs; verify migration is backwards-compatible before release. | Staging data and integrations are release-ready. | Do not change contracts without informing Dev 1. |
| 10 | release/api-v1.0.0 | Run final migration review, seed verification, API smoke tests, and post-release Zoho/Resend reconciliation. | Production API/integration verification recorded. | Provide operations field/status guide to CERA. |

5. Integration contracts and hand-offs

| Direction | Working agreement |
| --- | --- |
| Read from Dev 1 | Form fields, dashboard views, service filters, copy/status labels, and UI validation requirements. |
| Read from Dev 3 | Database/Valkey URLs, secret injection, Authentik issuer/client settings, deployment and backup constraints. |
| Provide to team | Versioned TypeScript contracts, seed data, API documentation, test accounts, and integration test evidence. |

6. Git and pull-request rules

Use conventional commits: feat(scope): description; fix(scope): description; test(scope): description; ci: description.

Keep PRs single-purpose. Include issue link, screenshots for UI work, tests run, migration impact, and rollback note where relevant.

Before PR: git fetch origin; git rebase origin/develop; resolve conflicts; run the relevant tests; push only your branch.

Never commit .env files, passwords, API keys, backups, real customer data, or production database dumps.

A database migration must be reversible or backward-compatible and reviewed by Dev 2 and Dev 3.

7. Day-10 release and post-launch responsibility

Freeze new feature work after Day 8. Only UAT defects, security fixes, and release documentation are allowed.

Create release/v1.0.0 from develop; deploy it to staging; run the complete smoke-test checklist.

CERA Product Owner records staging approval in the release issue; Dev 3 records technical approval.

Merge release/v1.0.0 to main, create annotated tag v1.0.0, and deploy the immutable image.

Watch GlitchTip, health checks, logs, Resend delivery, R2 access, and Zoho sync for the first 24 hours.

If a critical issue appears, create hotfix/<name> from main, test, release, and merge the fix back to develop.

Named developer: ______________________________     Date assigned: ______________________________