CERA MEDICAL  /  STACK & SCALE

Full Platform
10-Day Delivery Workbook

Developer 03 — Platform, Security & Release

Owns infrastructure, security, Authentik, Docker, CI/CD, staging/production releases, backups, and observability.

| Delivery control | Agreed working rule |
| --- | --- |
| Programme target | Complete the full CERA first-release platform in ten intense working days. Work is sliced vertically and integrated daily. |
| Branch base | All feature branches start from develop. main is production-only. No direct pushes to protected branches. |
| Required approvals | One PR approval minimum; two for authentication, database migrations, secrets, deployment, or security changes. |
| Definition of launch | Public services/blog, CMS, secure enquiry, customer status, staff workflow, Zoho, Resend, Authentik, R2, monitoring, backup and documented deployment all work in staging and production. |

1. Recommended project decisions

| Decision | Recommended direction |
| --- | --- |
| Customer journey | Browse public services and blog posts; submit a secure service enquiry; optionally create an account to view enquiry status and updates. Online payment is not in v1 until CERA selects a payment provider in writing. |
| Staff roles | Customer; Content Editor; Operations/Support; Administrator. Authentik enforces role-based access. |
| Data boundary | Collect only name, email, phone, selected service, message, consent, and enquiry status. Do not collect diagnosis, medical history, prescriptions, or health documents in v1. |
| Zoho records | Create/update Lead or Contact with full name, email, phone, selected service, source, consent timestamp, enquiry ID, owner, and status. |
| Content approval | CERA nominates one Content & Clinical Approver. No health claim, service description, blog, or public pricing is published without that person’s written approval. |
| Release approval | Dev 3 approves technical readiness. CERA’s nominated Product Owner approves staging/UAT. Production needs both approvals in GitHub. |
| Account ownership | CERA owns and pays all vendor accounts: Hetzner, Cloudflare, R2, GitHub, Resend, Zoho, domain, and backups. Developers receive only necessary role-based access. |
| Jurisdiction | Swabi, Khyber Pakhtunkhwa, Pakistan. |

2. Your ownership and boundaries

| Area | Your responsibility |
| --- | --- |
| Primary modules | Docker Compose; Hetzner CX43/CX33; Caddy; Cloudflare; GitHub Actions; Authentik; R2; GlitchTip; backups; release controls. |
| Key integrations | Provides secure deployment/runtime for Dev 1 and Dev 2 applications. |
| Review focus | Secrets, access rights, container hardening, health checks, data backups, migrations, release rollback, and incident response. |

3. Daily collaboration routine

09:30 — 15-minute stand-up: yesterday, today, blockers, files likely to conflict.

Before coding — read the assigned issue, acceptance criteria, and shared contract/type.

During coding — work only on the named branch; do not edit another developer’s active module without agreement.

Before PR — run lint, type-check, relevant tests, and manual local verification.

PR review — one approval minimum; two approvals for auth, database migrations, secrets, deployment, or security changes.

End of day — update the GitHub Issue, post staging link/test evidence where available, and name any hand-off needed tomorrow.

4. Ten-day build schedule

Each day ends with a pushed branch, updated issue, test evidence, and a clear hand-off. If a task cannot be completed, cut non-critical polish—not security, data ownership, test coverage, or release controls.

| Day | Branch | Build work | Done | Hand-off |
| --- | --- | --- | --- | --- |
| 1 | chore/infra-bootstrap | Create Client-owned accounts/projects; configure CX43 production and temporary CX33 staging; private networks, firewall baseline, SSH keys, Docker, and Caddy. | Both environments reachable through approved access only. | Never put credentials in GitHub issues, code, or chat. |
| 2 | ci/github-actions-pipeline | Create CI: install, lint, type-check, tests, build, Docker image, dependency checks. Configure protected main/develop and GitHub Environments. | PRs cannot merge without green checks. | Dev 1/2 add their test commands to CI. |
| 3 | feat/authentik-roles | Configure Authentik tenants/apps/clients, MFA for admins, roles for customer/editor/operations/admin, and login callback routes. | Role-based staging login works with test accounts. | Dev 1 integrates login; Dev 2 checks API claim validation. |
| 4 | feat/cloudflare-r2-caddy | Configure Cloudflare DNS/TLS, Caddy reverse proxy/security headers, R2 buckets/credentials, upload permissions, and no public DB/Valkey ports. | Staging uses HTTPS and protected service boundaries. | Confirm media flow with Dev 1. |
| 5 | feat/staging-deployment | Automate develop → staging deployment, image tags, health checks, migration sequence, and rollback to previous image. | Merged staging PR deploys predictably and smoke tests pass. | Dev 2 supplies migration command; Dev 1 supplies smoke paths. |
| 6 | feat/backup-restore | Enable Hetzner backups; add encrypted PostgreSQL backup to R2; document retention; perform a restore into staging. | Restore evidence and recovery steps documented. | No production health/patient data is used for development testing. |
| 7 | feat/glitchtip-observability | Configure GlitchTip projects, alert routing, structured logs, uptime/health endpoint checks, and release/version reporting. | A deliberate test error reaches GlitchTip with release version. | Each developer verifies errors are meaningful, not secret-bearing. |
| 8 | test/security-release-checks | Run access review, secret scan, dependency audit, firewall review, rate-limit/security-header checks, and disaster-recovery rehearsal. | Technical release gate is either approved or blocked with clear issues. | Log all release blockers in GitHub. |
| 9 | fix/uat-release | Support UAT fixes, verify image reproducibility, finalise production environment, and prepare rollback command/owner. | Production release checklist ready for CERA approval. | Only release-critical changes are accepted. |
| 10 | release/production-v1.0.0 | Approve GitHub production deployment, create tag, deploy, run smoke tests, monitor 24 hours, and hand over access/runbook. | Release record, rollback reference, and support handover completed. | Merge any hotfixes back to develop. |

5. Integration contracts and hand-offs

| Direction | Working agreement |
| --- | --- |
| Read from Dev 1 | Required routes, public/protected pages, image upload behaviour, and browser smoke tests. |
| Read from Dev 2 | Service health endpoints, migration commands, background jobs, database and Valkey requirements, webhook paths. |
| Provide to team | Environment contract, staging URL, GitHub Environment rules, deployment logs, backup runbook, and release checklist. |

6. Git and pull-request rules

Use conventional commits: feat(scope): description; fix(scope): description; test(scope): description; ci: description.

Keep PRs single-purpose. Include issue link, screenshots for UI work, tests run, migration impact, and rollback note where relevant.

Before PR: git fetch origin; git rebase origin/develop; resolve conflicts; run the relevant tests; push only your branch.

Never commit .env files, passwords, API keys, backups, real customer data, or production database dumps.

A database migration must be reversible or backward-compatible and reviewed by Dev 2 and Dev 3.

7. Day-10 release and post-launch responsibility

Freeze new feature work after Day 8. Only UAT defects, security fixes, and release documentation are allowed.

Create release/v1.0.0 from develop; deploy it to staging; run the complete smoke-test checklist.

CERA Product Owner records staging approval in the release issue; Dev 3 records technical approval.

Merge release/v1.0.0 to main, create annotated tag v1.0.0, and deploy the immutable image.

Watch GlitchTip, health checks, logs, Resend delivery, R2 access, and Zoho sync for the first 24 hours.

If a critical issue appears, create hotfix/<name> from main, test, release, and merge the fix back to develop.

Named developer: ______________________________     Date assigned: ______________________________