# 10-Working-Day Implementation Plan

Three-developer delivery plan for the CERA commerce + content first release

DELIVERY TARGET Ten working days is treated as the committed implementation window. It depends on day-one access to domain/DNS, hosting, repository, product catalogue, payment sandbox/merchant credentials, approved content and fast decisions. Client-side delays pause the affected dependency rather than silently reducing QA.

# 1. Team allocation

| Developer | Primary ownership |
| --- | --- |
| Developer A - Commerce / Backend / DevOps | Vendure, PostgreSQL, Redis/Valkey, product/order model, payment/shipping, R2 integration, Docker and server deployment. |
| Developer B - Frontend / UX | Next.js storefront, design system, homepage, catalogue/PDP, cart/checkout UI, services, blog frontend, responsive/SEO implementation. |
| Developer C - CMS / Identity / Observability | Payload CMS, Authentik, GlitchTip, Zoho/Resend DNS integration, admin access, analytics, content migration support and QA. |

# 2. Day-by-day plan

| Day | Primary outcome | Parallel work |
| --- | --- | --- |
| 1 | Infrastructure and application foundations | Repos, Docker, PostgreSQL/Redis, Vendure skeleton, Next.js/Payload skeleton, Caddy, Cloudflare/DNS plan. |
| 2 | Design system + commerce model | Navigation/components; product/variant/category/stock model; CMS collections and admin access foundation. |
| 3 | Homepage, catalogue, services/blog structure | Homepage sections; catalogue/category/search; service/article models; R2 media path. |
| 4 | PDP + cart + content rendering | Product detail/variant UX; cart logic; blog/service SSR pages; author/category relationships. |
| 5 | Checkout + shipping + payment | Guest/customer flow, shipping rules, COD/bank transfer and one online gateway path if credentials are ready. |
| 6 | Orders/admin + identity hardening | Order lifecycle, admin workflows, Authentik access gateway, role review, transactional email templates. |
| 7 | CMS completion + R2 + SEO | Publishing workflow, media, metadata, sitemap/structured data, related articles/services, legal/basic static pages. |
| 8 | Integrations + feature freeze | Resend/Zoho DNS, analytics/Search Console/Clarity, GlitchTip, backup jobs; no new major features after this day. |
| 9 | Full QA / UAT / fixes | Checkout/payment tests, roles, email, mobile/accessibility, SEO crawl, backup restore, security and performance fixes. |
| 10 | Production launch + handover | DNS cutover, production smoke tests, admin training, monitoring confirmation, documentation/access handover. |

# 3. Mandatory client inputs

Current domain registrar and DNS access.

Product catalogue: names, SKUs, variants, prices, stock, descriptions, images, approved claims/warnings and shipping/return eligibility.

One selected online payment gateway merchant/sandbox account plus COD/bank-transfer rules.

Shipping zones/rates and fulfilment owner.

Final logo/brand assets and approved website copy or explicit approval to use agreed draft content.

Zoho and Resend account ownership/verification access.

Named CERA approver available for same-day decisions during the 10-day window.

# 4. Scope protection

Feature freeze at end of Day 8.

Days 9-10 are reserved for QA, production release and handover.

New requirements that materially change checkout, data model, CMS structure or integrations are logged for the next iteration unless replacing an unfinished equivalent item.

Research CRM/proposal workflows are not part of this release.

# 5. Daily operating cadence

15-minute internal developer sync each morning.

Shared issue board with owner, status and blocker.

One end-of-day integrated build from Day 2 onward.

Client review checkpoints on Days 3, 6, 8 and 9.

No code is considered complete until merged, deployed to staging and smoke-tested.